## How to use
Factory acceptance test (FAT) checklist and record
From ZeroLine: zerolineai.com/guides/factory-acceptance-test-checklist/ (October 2026). Free to use and adapt.
What is in this workbook
Checklist: 30 checks for a machine or production line in three groups (configuration and safety, process and traceability, handover and shipment).
Acceptance limits: the six numbers to agree in the contract before the build starts. The example values are for a battery PACK line; replace them with yours.
Performance run: a blank 8 x 120-minute run sheet. Type packs, stops and first-pass results per block; output, yield, stop ratio and OEE calculate themselves.
Example run A and B: a worked example of two runs on an 8 PPM energy-storage PACK line, a failed first run and a passed retest.
NCR register and Acceptance record: log every nonconformity with owner, deadline and retest, and sign the final record.
Rules that keep a FAT honest
1. Agree the checklist and the numeric limits in the contract, before the build. A limit agreed during the test is a negotiation, not an acceptance criterion.
2. Freeze the recipe, hardware, PLC/HMI versions and tool calibration before each run. Record what was frozen.
3. Count unique, first-time completed units at the line exit over the whole window, stops included. Reworked units never return to the first-pass count.
4. Enter N/A only with a written reason and the buyer's approval.
5. No open Critical or Major nonconformity at sign-off. Minor items need an owner, a deadline and an agreed way to close them.
6. Technical acceptance, payment and shipment are separate decisions. A FAT pass is not a product certificate and does not replace the site acceptance test (SAT).
Yellow cells are for your entries. The limits, formulas and example values are a starting point, not advice for a specific contract; your drawings, approved test procedures, applicable standards and the signed technical agreement govern the test.

## Checklist
Group | ID | Check | Acceptance criterion | Evidence to attach | Run 1 result | Final result | Evidence file / timestamp | NCR | Notes
Configuration and safety | 01 | Contract baseline | Approved layout, bill of materials, product drawings, critical-to-quality features and revisions match the installed scope. | Signed protocol and revision list
Configuration and safety | 02 | Identity and substitutions | Serial numbers and key component brands match the contract; every substitution has written approval. | Machine identities, nameplate photos
Configuration and safety | 03 | Utilities and interfaces | Actual power, frequency, air and network conditions recorded; upstream and downstream handshakes verified. | Utilities log
Configuration and safety | 04 | Tools and metrology | Calibration dates, range and resolution of the torque, leak, electrical and weld test equipment suit the approved tests. | Calibration certificates
Configuration and safety | 05 | Guarding and access | Guarding, closed laser enclosures and access control follow the reviewed safety design. | Safety design review, photos
Configuration and safety | 06 | Emergency stop | Each stop circuit reaches its defined safe state; reset alone does not restart motion. | Timestamped video, witness record
Configuration and safety | 07 | Guard restart sequence | Closing a guard, reset and a deliberate start stay three separate actions. One failed challenge puts the test on hold. | Timestamped video, witness record
Configuration and safety | 08 | Utility loss and recovery | After a controlled power or air loss the line recovers by the approved sequence, with no unintended restart. | Timestamped video
Configuration and safety | 09 | Reject and buffer logic | A defective unit cannot advance as good; blocked and starved interfaces keep each unit's identity and state. | Challenge log
Configuration and safety | 10 | Dry run and modes | Manual, setup and automatic modes, alarms and recipe selection behave as approved. | Video, alarm list
Process and traceability | 11 | Cell identity and polarity | Cell-to-module-to-pack genealogy is complete; polarity and identification challenges are caught. | Serial-level genealogy export
Process and traceability | 12 | Weld qualification | Joints tested to the approved drawing, method and force limit; each joint type has its own qualified limit. | Weld coupon report
Process and traceability | 13 | Weld monitoring | Recipe, joint identity, alarms and reject status are recorded for every weld; strength is not judged by appearance alone. | Weld data export
Process and traceability | 14 | Fastening records | Every specified fastener has a traceable torque/angle result before the unit is released as good. | Torque export
Process and traceability | 15 | Leak testing | Approved test pressure and limit; known-good and known-leak masters are classified correctly. | Master check log
Process and traceability | 16 | Electrical end-of-line test | Approved polarity, insulation, dielectric and functional recipes, run by qualified people. | EOL export
Process and traceability | 17 | Duplicate serial control | A repeated identifier is rejected; an old pass record cannot be reused for a new unit. | Challenge log
Process and traceability | 18 | Network and database loss | Offline handling keeps the records; recovery reconciles units without duplicates. | Recovery log
Process and traceability | 19 | Throughput and stability | Full run witnessed with its real duration and denominator; unplanned stops and all quality causes stay in the report. | Output and downtime log, WIP reconciliation
Process and traceability | 20 | Recipe changeover | Last-good to first-good time recorded and recipe interlocks confirmed against the agreed target. | Changeover log
Handover and shipment | 21 | English HMI and alarms | Approved English messages and reset instructions on every screen and in the manual. | HMI screenshots, alarm appendix
Handover and shipment | 22 | Software handover | PLC/HMI project files, versions, licences, backups and access responsibilities documented. | Software package list
Handover and shipment | 23 | Backup restoration | The agreed restore method is demonstrated; recipes and traceability data are valid afterwards. | Restore log
Handover and shipment | 24 | Remote access | Buyer-approved access method, permissions and account handover; no undocumented default account. | Access list
Handover and shipment | 25 | Drawings and manuals | As-built electrical, pneumatic, mechanical and layout files match the final configuration. | As-built file set
Handover and shipment | 26 | Spares and training | Wear parts and special tools reconciled; operator and maintenance training scope recorded. | Spares list, training record
Handover and shipment | 27 | Compliance evidence | Documents for the destination market checked for scope and issuer. A FAT pass is not a certificate. | Certificates, test reports
Handover and shipment | 28 | Packing and preservation | Split points, lifting, fixtures and protection approved; final packing inspection is a later gate. | Packing plan
Handover and shipment | 29 | Installation and SAT | Site utilities, interfaces, commissioning duties and the tests deferred to the site acceptance test recorded. | SAT plan
Handover and shipment | 30 | Commercial release | Only the buyer authorises the payment and shipment milestone, after the required closure. | Buyer authorisation

## Acceptance limits
Criterion | Example limit (battery PACK line, 8 cells/min design rate) | Your agreed limit | Measured | Pass / Fail
Sustained gross output | At least 7.60 cell equivalents per minute, i.e. at least 152 completed 48-cell packs in a 960-minute window (95% of the 8 cells/min design rate).
First-pass yield | At least 99.00%, all quality causes included. A reworked unit never returns to the first-pass count.
Unplanned stop ratio | No more than 2.00% of the 960-minute window.
Output interval, 95th percentile | No more than 390 seconds between completed packs (design 360 s), nearest-rank percentile over all intervals, stops included.
Safety and traceability | Every prescribed safety challenge passes; no unexpected restart; every unit has its required traceability data.
Closure | No open Critical or Major nonconformity. Minor items have a written owner, deadline and buyer-agreed closure route.
These limits belong to the worked example. IEC 62381 and other FAT standards do not set output or yield numbers; your signed technical agreement does.

## Performance run
Units of | 48 | cells per completed unit
Ideal cycle (min/unit) | 6 | design output interval: 360 s per 48-cell pack at 8 cells/min
Block | Minutes | Unplanned stop min | Completed units | First-pass good | First-pass fail | FPY
1 | 120
2 | 120
3 | 120
4 | 120
5 | 120
6 | 120
7 | 120
8 | 120
Total
Metric | Result | Formula
Gross output (units/min) |  | Completed units / window minutes
Cell equivalents per minute |  | Completed units x cells per unit / window minutes; not a measured loader rate
Elapsed mean (s per unit) |  | Window seconds / completed units
Unplanned stop ratio |  | Stop minutes / window minutes
Availability |  | (Window - stop minutes) / window
Performance |  | Completed units x ideal cycle / run time
Quality (first-pass yield) |  | First-pass good / completed units
OEE |  | First-pass good x ideal cycle / window = availability x performance x quality
Output interval P95 (s), from the line exit log
Count unique, first-time completed units at the final line exit over the full window, stops included. Reconcile opening and closing work in progress. Startup, safety challenges and destructive tests are separate from this window.

## Example run A
Units of | 48 | cells per completed unit
Ideal cycle (min/unit) | 6 | design output interval: 360 s per 48-cell pack at 8 cells/min
Block | Minutes | Unplanned stop min | Completed units | First-pass good | First-pass fail | FPY
1 | 120 | 0 | 20 | 20
2 | 120 | 5 | 19 | 18
3 | 120 | 5 | 19 | 18
4 | 120 | 10 | 18 | 17
5 | 120 | 0 | 20 | 19
6 | 120 | 5 | 19 | 19
7 | 120 | 0 | 20 | 19
8 | 120 | 5 | 19 | 19
Total
Metric | Result | Formula
Gross output (units/min) |  | Completed units / window minutes
Cell equivalents per minute |  | Completed units x cells per unit / window minutes; not a measured loader rate
Elapsed mean (s per unit) |  | Window seconds / completed units
Unplanned stop ratio |  | Stop minutes / window minutes
Availability |  | (Window - stop minutes) / window
Performance |  | Completed units x ideal cycle / run time
Quality (first-pass yield) |  | First-pass good / completed units
OEE |  | First-pass good x ideal cycle / window = availability x performance x quality
Output interval P95 (s), from the line exit log | 480
WORKED EXAMPLE, storage PACK line. Run A: 154 packs, FPY 96.75%, stop ratio 3.13%, output interval P95 480 s. Decision: HOLD (safety challenge, yield, stops and P95 failed; gross output passed).

## Example run B
Units of | 48 | cells per completed unit
Ideal cycle (min/unit) | 6 | design output interval: 360 s per 48-cell pack at 8 cells/min
Block | Minutes | Unplanned stop min | Completed units | First-pass good | First-pass fail | FPY
1 | 120 | 0 | 20 | 20
2 | 120 | 0 | 20 | 20
3 | 120 | 3 | 19 | 19
4 | 120 | 0 | 20 | 20
5 | 120 | 0 | 20 | 19
6 | 120 | 4 | 19 | 19
7 | 120 | 0 | 20 | 20
8 | 120 | 0 | 20 | 20
Total
Metric | Result | Formula
Gross output (units/min) |  | Completed units / window minutes
Cell equivalents per minute |  | Completed units x cells per unit / window minutes; not a measured loader rate
Elapsed mean (s per unit) |  | Window seconds / completed units
Unplanned stop ratio |  | Stop minutes / window minutes
Availability |  | (Window - stop minutes) / window
Performance |  | Completed units x ideal cycle / run time
Quality (first-pass yield) |  | First-pass good / completed units
OEE |  | First-pass good x ideal cycle / window = availability x performance x quality
Output interval P95 (s), from the line exit log | 378.95
WORKED EXAMPLE, storage PACK line. Run B, after corrections: 158 packs, FPY 99.37%, stop ratio 0.73%, output interval P95 378.95 s. Decision: performance limits met; technical acceptance after regression checks and document closure.

## NCR register
NCR | Severity | Check ID | Finding | Correction | Owner | Deadline | Retest method and result | Reviewer | Status
Rows 3-9: the worked example. Delete them and log your own from row 10.
NCR01 | Critical | 07 | Closing a guard started the line unexpectedly in 1 of 12 controlled challenges. | Separate reset and start logic; freeze the corrected safety configuration. | Controls lead | Day 1 | 20/20 targeted restart challenges and 40/40 safety regression checks passed. |  | Closed
NCR02 | Major | 12, 13 | Two pack weld alarms; 2 of 30 coupons below the 450 N reference joint limit. | Correct clamp alignment and requalify the weld recipe. | Process lead | Day 2 | 30/30 new coupons passed, minimum 496 N; no recurrence in 158 packs of run B. |  | Closed
NCR03 | Major | 14 | One pack released without its fastening result. | Good-release interlock now requires every expected fastening record. | Controls and quality | Day 2 | 10 missing-record challenges blocked; 50/50 sampled pack records complete. |  | Closed
NCR04 | Major | 15 | One pack rejected at the leak test; worn fixture seal. | Replace the fixture seal; validate the master procedure. | Test lead | Day 2 | Known-good and known-leak masters 20/20 each classified correctly. |  | Closed
NCR05 | Major | 17 | A repeated pack identifier was accepted at end of line. | Enforce uniqueness; block reuse of an earlier pass. | MES lead | Day 2 | 10/10 duplicate challenges blocked; 50/50 records uniquely linked. |  | Closed
NCR06 | Major | 19 | Stop ratio 3.13% and output interval P95 480 s exceed the limits. | Correct the buffer handshake and downstream recovery sequence. | Integration lead | Day 2 | Full run B: 7 stop minutes (0.73%), P95 378.95 s, 7.90 cell equivalents/min. |  | Closed
NCR07 | Minor | 21 | Two alarm reset instructions missing from the English manual. | Revise the English alarm appendix; cross-check the HMI revision. | Documentation lead | Day 4 | Buyer document review closed both entries. |  | Closed Day 4

## Acceptance record
Factory acceptance record
Project / PO
Equipment / serial numbers
Protocol revision
Product / recipe
Test dates
Location (factory) and witnesses
Witnessed in person or by live video
Checklist result (checks passed / total)
Acceptance limits result
Open items (Minor only) with owner and deadline
Evidence file location
Disposition (Hold / Conditional / Pass)
Supplier representative, signature, date
Buyer witness, signature, date
Technical acceptance does not authorise payment or shipment by itself; the buyer approves those separately. Site acceptance (SAT) follows installation.